## in
country | iso3c | year | date | status_new | census_round | updated_status | updated_status_note
Benin | BEN | 2023 | -2023 | Planned | 2020 | Likely planned | It seems like as of March 2023, they were developing committees for the census https://www.gouv.bj/article/2152/rgph5-installation-membres-comite-national-sous-comites-recensement-prevue-mardi-14-mars-2023/
Central African Republic | CAF | 2023 | (December 2023) | Planned | 2020 | Planned | Based on news from last month, the government is preparing for the census round so that it completes end of year 2023/early 2024 https://corbeaunews-centrafrique.org/la-rca-se-prepare-pour-son-quatrieme-recensement-general-de-la-population/
Congo | COG | 2023 | -2023 | Planned | 2020 | Conducting | Enumeration launched in April 2023, finished in May. Not sure of the current status: https://ins-congo.cg/recensement/
Djibouti | DJI | 2023 | -2023 | Planned | 2020 | Completed | Completed as of yesterday: https://twitter.com/3eRGPHdjibouti/status/1704492681043333522
Gabon | GAB | 2023 | -2023 | Planned | 2020 | Conducting | It looks like it is being conducted: https://instatgabon.org/rgpl-2023/
Gambia | GMB | 2023 | (November 2023) | Planned | 2020 | Planned | The Gambia Bureau of Statistics website published an article in August stating that the census is rescheduled from April 2023 to November 2023: https://www.gbosdata.org/news/10-rescheduling-of-the-2023-population-and-housing
Guinea Bissau | GNB | 2023 | -2023 | Planned | 2020 | Conducting | https://www.afristat.org/lancement-du-recensement-de-la-population-de-guinee-bissau/
Mauritania | MRT | 2023 | (November 2023) | Planned | 2020 | Planned | Scheduled for Nov 2023 https://kassataya.com/2023/06/15/mauritanie-recensement-general-de-la-population-et-de-lhabitat-rgph-en-novembre-2023/
Namibia | NAM | 2023 | (18 September 2023) | Planned | 2020 | Conducting | Based on this press release https://nsa.nsa.org.na/census-page-2
Niger | NER | 2023 | -2023 | Planned | 2020 | Planned | Looks like it is still in the piloting phase-- it hasn't been fully launched yet https://www.stat-niger.org/?cat=69
Nigeria | NGA | 2023 | (3 May 2023) | Planned | 2020 | Planned | Looks like it hasn't been launched yet http://2023census.gov.ng/
Sao TomÃ© and PrincipÃ© | STP | 2023 | -2023 | Planned | 2020 | Planned | Postponed to 2024 https://saotomeandprincipe.unfpa.org/pt/news/recenseamento-geral-da-popula%C3%A7%C3%A3o-e-habita%C3%A7%C3%A3o-adiado-para-2024
Senegal | SEN | 2023 | (June 2023) | Planned | 2020 | Conducting | See https://www.ansd.sn/actualite/prolongation-du-recensement-jusquau-20-juin-2023
United Republic of Tanzania | TZA | 2023 | (23 August 2023) | Planned | 2020 | Completed | Looks like it was completed in 2022? https://sensa.nbs.go.tz/
Antigua and Barbuda | ATG | 2023 | (October 2023) | Planned | 2020 | Planned | No updates, just that it was postponed to 2023: https://statistics.gov.ag/census/
British Virgin Islands | VGB | 2023 | (15 June 2023) | Planned | 2020 | Conducting | https://bvi.gov.vg/media-centre/statement-deputy-premier-population-and-housing-census-2023
Cuba | CUB | 2023 | -2023 | Planned | 2020 | Planned | Postponed to 2025 https://www.elpais.cr/2023/05/22/cuba-anuncia-para-2025-censo-poblacional-postergado-en-2022-por-crisis-economica/
CuraÃ§ao | CUW | 2023 | (2 September 2023) | Planned | 2020 | Conducting | https://senso.cbs.cw/information-on-the-2023-census
El Salvador | SLV | 2023 | (May 2023) | Planned | 2020 | Planned | Looks like the census will happen in 2024, as the government is first undergoing cartography updates https://www.elsalvador.com/noticias/negocios/actualizacion-cartografica-inicia-este-mes-en-el-salvador/1088729/2023/
Honduras | HND | 2023 | -2023 | Planned | 2020 | Planned | Looks like it hasn't been launched yet, but there is a development of a committee https://ine.gob.hn/v4/2023/06/29/ine-oficializa-el-comite-consultivo-asesor-del-xviii-censo-de-poblacion-y-vii-de-vivienda/
Montserrat | MSR | 2023 | -2023 | Planned | 2020 | Conducting | https://www.gov.ms/2023/07/21/statistics-department-of-montserrat-launches-2023-population-and-housing-census/
Nicaragua | NIC | 2023 | -2023 | Planned | 2020 | Planned | Looks like it is set for 2024 https://www.swissinfo.ch/spa/nicaragua-censo_nicaragua-censar%C3%A1-a-su-poblaci%C3%B3n-despu%C3%A9s-de-18-a%C3%B1os/48721608
St. Vincent and the Grenadines | VCT | 2023 | -2023 | Planned | 2020 | Planned | Looks like it is set for 2023 https://stats.gov.vc/2023-population-and-housing-census/
Trinidad and Tobago | TTO | 2023 | -2023 | Planned | 2020 | Planned | Looks like it is still being planned https://www.planning.gov.tt/content/media-release-cso-use-technology-manage-cost-population-and-housing-census and https://www.planning.gov.tt/content/statistics-focus-trinidad-and-tobagos-national-population-and-housing-census
Turks and Caicos Islands | TCA | 2023 | -2023 | Planned | 2020 | Conducting | https://suntci.com/tcis-population-and-housing-census-officially-launched-p9078-129.htm
Suriname | SUR | 2023 | -2023 | Planned | 2020 | Unsure | Unable to find info online
India | IND | 2023 | (April 2023) | Planned | 2020 | Planned | Postponed to at least September 30 2023: https://www.wionews.com/india-news/indias-first-digital-census-remains-postponed-till-september-2023-550272
Iraq | IRQ | 2023 | -2023 | Planned | 2020 | Planned | News article on May 7, 2023 says that the Iraqi ministry of planning says it needs 15 months to conduct the census: https://www.rudaw.net/english/middleeast/iraq/07052023
Sri Lanka | LKA | 2023 | -2023 | Planned | 2020 | Planned | Set to commence at the end of 2023 follow by enumeration phase in 2024: http://www.statistics.gov.lk/Blog/Blog_details#
United Arab Emirates | ARE | 2023 | -2023 | Planned | 2020 | Conducting and planned | Looks like census is being conducted by Emirate, look at separate articles of Ras al Khaimah, Sharjah-- https://www.google.com/search?sca_esv=567294360&sxsrf=AM9HkKnwULMYBfbr4phx925RZOqdk8W2wg:1695320148442&q=uae+census+population+census&tbm=nws&source=lnms&sa=X&ved=2ahUKEwinyOnZp7yBAxVxHTQIHeuCBfAQ0pQJegQISxAB&biw=1289&bih=707&dpr=2
Uzbekistan | UZB | 2023 | (November 2023) | Planned | 2020 | Planned | Scheduled for Nov 2023 https://yuz.uz/en/news/v-uzbekistane-perepis-naseleniya-budet-provedena-2023-godu
Albania | ALB | 2023 | (September 2023) | Planned | 2020 | Planned or conducting? | https://www.instat.gov.al/en/census-2023/about/what-is-the-census/
Bosnia and Herzegovina | BIH | 2023 | (October 2023) | Planned | 2020 | Potentially planned | It's quite politicized https://sarajevotimes.com/in-the-years-ahead-bosnia-will-have-15-million-inhabitants/
Montenegro | MNE | 2023 | -2023 | Planned | 2020 | Planned | NSO website says the census will be implemented as of 31 October 2023 at midnight: https://www.monstat.org/eng/page.php?id=1758&pageid=1758
Republic of Moldova | MDA | 2023 | (28 Aug - 10 Oct 2023) | Planned | 2020 | Planned | Pilot census is happening now: https://statistica.gov.md/en/the-population-and-housing-pilot-census-will-take-place-from-12_60629.html
Micronesia, Federated States of | FSM | 2022 | -2022 | Planned | 2020 | Planned | Pacific Community Statistics for Development division census calender shows that there is a calender planned for the Federated States of Micronesia in 2023: https://sdd.spc.int/census-and-survey-calendar
Tokelau | TKL | 2022 | -2022 | Planned | 2020 | Planned | No info about it on the Tokelau Government census page, 2016 is most recent one https://www.tokelau.org.nz/Tokelau+Government/Government+Departments/Office+of+the+Council+for+the+Ongoing+Government+OCOG/Tokelau+National+Statistics+Office/census.html but there is a 2022 census entry in this calendar for Tokelau https://sdd.spc.int/census-and-survey-calendar
Tuvalu | TUV | 2022 | -2022 | Planned | 2020 | Planned | Last post on NSO website about this was August 2022, and under the census and survey archives the last available census data appears to be from 2017: https://stats.gov.tv/news/recruiting-fieldworkers-for-lfc/